## Sheet1
Conestoga College
Team: | Nicholas Lee, Cynthia Cheng, Thomas Craig, Chris Banks
Agile Product Feature List - Backlog
Note: PD = Person day = 4 hours
# | Description | Priority | PD Est. | Completion Date Est. | By
…
Iteration 2
108 | Schedule Resource for Work Order (Gantt Chart) | High | 4 | 2019-02-15 | NL, CC, TC, CB
109 | Schedule Technician for Work Order (Gantt Chart) | High | 4 | 2019-02-15 | NL, CC, TC, CB
110 | Cancel Work Order Assignment of Resource (Gantt Chart) | Medium | 4.5 | 2019-02-15 | NL, CC, TC, CB
111 | Cancel Work Order Assignment of Technician (Gantt Chart) | Medium | 4.5 | 2019-02-15 | NL, CC, TC, CB
112 | Work Order time slot is updated (Gantt Chart) | Medium | 4 | 2019-02-15 | NL, CC, TC, CB
113 | View a single date in Gantt Chart | Medium | 3.5 | 2019-02-15 | NL, CC, TC, CB
114 | View multiple dates Gantt Chart | High | 3.5 | 2019-02-15 | NL, CC, TC, CB
116 | View Assigned Work Order Information | Medium | 1.5 | 2019-02-15 | NL, CC, TC, CB
…
Iteration 3
117 | User Automatic Scheduling | High | 5 | 2019-02-15 | NL, CC, TC, CB
118 | View Location Mapping | Medium | 4 | 2019-02-15 | NL, CC, TC, CB
119 | View Technician or Resource ETA | High | 4 | 2019-02-15 | NL, CC, TC, CB
…