## Sheet1
Conestoga College
Team: | Nicholas Lee, Cynthia Cheng, Thomas Craig, Chris Banks
Release Plan Summary
|  | Iteration #1 | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  |  | Due: Feb-19 |  | Due: Mar-8 | Due: Apr-24
|  | Estimated | Actual | Estimated | Actual
# | Feature / Requirement
101 | View Scheduler Dashboard | 1 | 6
102 | Add a Work Order | 1 | 2.25
103 | View Work Order Details | 1.25 | 7.25
104 | Update a Work Order | 1.25 | 2.75
105 | Cancel a Work Order | 1.5 | 2
106 | Filter Work Order List | 1.5 | 4.25
107 | Search for a Work Order By ID | 1.5 | 3.5
115 | Dispatch Schedule | 1.25 | 2.75
120 | View Recommended Technicians/Resources | 3 | 4.25
121 | Assign a Technician to Work Order (Testing) | 1.5 | 3.25
122 | Assign a Resource to Work Order (Testing) | 1.5 | 3.25
108 | Schedule Resource for Work Order (Gantt Chart) |  |  | 4
109 | Schedule Technician for Work Order (Gantt Chart) |  |  | 4
110 | Cancel Work Order Assignment of Resource (Gantt Chart) |  |  | 4.5
111 | Cancel Work Order Assignment of Technician (Gantt Chart) |  |  | 4.5
112 | Work Order Time Slot is Updated (Gantt Chart) |  |  | 4
113 | View a Single Date in Gantt Chart |  |  | 3.5
114 | View Multiple Dates in Gantt Chart |  |  | 3.5
116 | View Assigned Work Order Information |  |  | 1.5
…
…
| Work Effort in Person Days (PD) | 16.25 | 41.5 | 29.5 | 0 | 0 | Target: 135 to 150 PD for team of 3
Given: 1 PD = 4 hours
| Total Estimated PD | 16.25 |  |  |  |  | Estimate: 3 PD per week = 45 PD per member; 135 PD for team of 3
| Total Actual PD | 41.5